## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Study LLM evaluation techniques, hallucination detection methods, RAG architecture, and existing evaluation frameworks (RAGAS, TruLens) | Must Have | None | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-02 | Design system architecture, agent responsibilities, scoring dimensions, orchestration flow, and data models | Must Have | US-01 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-03 | Develop Evaluation Input Module - single submission interface accepting question, AI response, and reference answer | Must Have | US-02 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-04 | Build Reference Knowledge Base - seed with SQuAD (and Wikipedia), implement chunking, embedding, and vector store indexing in ChromaDB | Must Have | US-02 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-05 | Build Retrieval Agent to fetch top-k relevant context chunks for a given question from ChromaDB | Must Have | US-04 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-06 | Build prototype Evaluation Agent using RAGAS semantic similarity for relevance, accuracy, completeness, and faithfulness scoring | Must Have | US-05 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-07 | Build frontend dashboard (HTML/CSS/JS) to submit evaluations and display scores | Should Have | US-03 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-08 | Build Relevance Judge Agent - scores response relevance to question on a defined scale with reasoning explanation per evaluation | Must Have | US-06 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-09 | Build Accuracy Judge Agent - checks factual correctness against reference answer or retrieved source chunks, outputs accuracy score with supporting evidence | Must Have | US-06 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-10 | Build Hallucination Detection Agent - identifies unsupported claims by cross-referencing response against RAG-retrieved source content, flags specific hallucinated statements | Must Have | US-06 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-11 | Validate individual agent scoring consistency and reasoning quality across varied question-answer pairs from benchmark datasets (SQuAD) | Must Have | US-08, US-09, US-10 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-12 | Validate individual agent scoring consistency and reasoning quality across varied question-answer pairs from benchmark datasets (SQuAD) | Must Have | US-08, US-09, US-11 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-13 | Validate individual agent scoring consistency and reasoning quality across varied question-answer pairs from benchmark datasets (SQuAD) | Must Have | US-08, US-09, US-12 | Ghayathri Devi G M | Done
Sprint 2 | Sprint 2 | US-14 | Redesign dashboard UI - tabbed navigation, reasoning/evidence display, hallucination flagged statements list | Must Have | US-08, US-09, US-10 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-15 | Build Completeness Judge Agent - assesses whether all aspects of the question are addressed, identifies specific omissions with reasoning | Must Have | US-08, US-09, US-10 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-16 | Build Verdict Agent - aggregates all dimension scores using a weighted scoring model, produces an overall quality verdict with a consolidated reasoning summary | Must Have | US-15 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-17 | Develop Per-Dimension Scoring Display - clean evaluation result interface showing individual agent scores, reasoning, flagged hallucinations, and overall verdict per submission | Should Have | US-16 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-18 | Build Batch Evaluation Module - user uploads a CSV of question-answer pairs, system evaluates all entries automatically and displays aggregated results | Must Have | US-15, US-16 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-19 | Fix Hallucination Detection Agent to check claims against the reference answer in addition to retrieved context, correcting false-positive flags | Should Have | US-10 | Ghayathri Devi G M | Done
Sprint 3 | Sprint 3 | US-20 | Optimize batch evaluation performance via concurrent per-row agent execution | Could Have | US-18 | Ghayathri Devi G M | Done
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 47.5 | 0 | 2 | 3.5 | 4.5 | 7.5 | 3.5 | 6.5 | 6.5 | 7 | 0.5 | 1 | 4.5 | 1 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Research LLM evaluation techniques and RAG architecture | 2026-06-30 | 2026-06-30 | Ghayathri | Research | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Review RAGAS and TruLens documentation | 2026-06-30 | 2026-07-01 | Ghayathri | Research | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Design high-level architecture and orchestration flow diagram | 2026-07-01 | 2026-07-01 | Ghayathri | Design | Done | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Define agent responsibilities, scoring dimensions, and data models | 2026-07-01 | 2026-07-02 | Ghayathri | Design | Done | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-05 | Build FastAPI /evaluate endpoint with input validation | 2026-07-02 | 2026-07-02 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Load SQuAD dataset and generate embeddings with Sentence-Transformers | 2026-07-03 | 2026-07-03 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-07 | Index embeddings into ChromaDB persistent vector store | 2026-07-03 | 2026-07-04 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-08 | Build retrieval_agent.py to query ChromaDB by question embedding | 2026-07-04 | 2026-07-04 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-09 | Integrate RAGAS SemanticSimilarity metric for relevance/accuracy/completeness | 2026-07-05 | 2026-07-06 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-06 | T-10 | Integrate Groq LLM-as-judge call for faithfulness / hallucination risk | 2026-07-06 | 2026-07-07 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US-07 | T-11 | Build HTML/CSS/JS dashboard and wire to /evaluate API | 2026-07-07 | 2026-07-08 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
US-03 | T-12 | Enable CORS middleware for frontend-backend communication | 2026-07-08 | 2026-07-08 | Ghayathri | Bug Fix | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-06 | T-13 | End-to-end testing of input, retrieval, and evaluation pipeline | 2026-07-09 | 2026-07-09 | Ghayathri | Testing | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SPRINT 2 BACKLOG
US-08 | T-14 | Build relevance_agent.py - Groq LLM call scoring relevance with reasoning, local fallback on failure | 2026-07-13 | 2026-07-13 | Ghayathri | Development | Done | 1.5 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-15 | Wire relevance_agent into main.py and database.py | 2026-07-13 | 2026-07-13 | Ghayathri | Development | Done | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-16 | Build accuracy_agent.py - claim-by-claim factual check with quoted supporting evidence | 2026-07-14 | 2026-07-14 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-17 | Fix JSON parsing errors from unescaped quotes in LLM output; add retry-before-fallback | 2026-07-14 | 2026-07-15 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-18 | Recalibrate accuracy scoring to separate CONTRADICTED vs UNSTATED-but-reasonable claims | 2026-07-15 | 2026-07-15 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-19 | Build hallucination_agent.py - claim-level flagging of unsupported statements against retrieved context | 2026-07-16 | 2026-07-16 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-20 | Add grounding safety-net (string-match verification) to catch LLM false-positive flags | 2026-07-16 | 2026-07-16 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-21 | Build validate_agents.py - runs all 3 agents on SQuAD correct/wrong pairs, checks scoring consistency and reasoning quality | 2026-07-17 | 2026-07-17 | Ghayathri | Testing | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0
US-12 | T-22 | Make reference_answer and source_pdf optional (Form/File fields) in /evaluate endpoint | 2026-07-18 | 2026-07-18 | Ghayathri | Development | Done | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-23 | Migrate evaluation history storage from SQLite to Supabase | 2026-07-19 | 2026-07-19 | Ghayathri | Development | Done | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-24 | Redesign dashboard into tabbed Dashboard/Retrieval/History views with brighter reasoning text | 2026-07-20 | 2026-07-20 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 3 BACKLOG
US-15 | T-25 | Build completeness_agent.py - claim-by-claim required-aspect check with missing_aspects list | 2026-07-21 | 2026-07-21 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-26 | Wire completeness_agent into main.py, database.py, and dashboard UI | 2026-07-21 | 2026-07-21 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-27 | Build verdict_agent.py - weighted aggregation (Accuracy 35%, Hallucination 30%, Relevance 20%, Completeness 15%) with verdict label and summary | 2026-07-22 | 2026-07-22 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-28 | Replace inline overall-score math in main.py with verdict_agent.build_verdict() | 2026-07-22 | 2026-07-22 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-29 | Redesign dashboard with a dedicated Verdict card (color-coded by label) and 4-agent metric grid | 2026-07-25 | 2026-07-25 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-30 | Build batch_evaluator.py - CSV parsing, per-row pipeline execution, aggregate stats | 2026-07-28 | 2026-07-28 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-31 | Add /batch-evaluate endpoint and Batch tab UI (upload, aggregate cards, per-row results table) | 2026-07-28 | 2026-07-28 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-32 | Add json_repair fallback and shorten required output length to fix recurring accuracy_agent JSON parse failures | 2026-07-30 | 2026-07-30 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-19 | T-33 | Fix hallucination_agent to check claims against reference_answer as well as retrieved context | 2026-07-30 | 2026-07-30 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-20 | T-34 | Parallelize the 4 independent per-row agent calls in batch_evaluator.py using ThreadPoolExecutor | 2026-08-02 | 2026-08-02 | Ghayathri | Bug Fix | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
US-18 | T-35 | Add Candidate Answer column to batch results table | 2026-08-02 | 2026-08-02 | Ghayathri | Bug Fix | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 (30 Jun) | None | N/A
Sprint 1 | Day 2 (1 Jul) | None | N/A
Sprint 1 | Day 3 (2 Jul) | None | N/A
Sprint 1 | Day 4 (3 Jul) | HuggingFace dataset 'squad' failed to resolve (HfUriError) | Switched to namespaced dataset name 'rajpurkar/squad'
Sprint 1 | Day 5 (4 Jul) | None | N/A
Sprint 1 | Day 6 (5 Jul) | RAGAS defaulted to OpenAI embeddings, missing API key error | Passed local Sentence-Transformers embeddings explicitly into evaluate()
Sprint 1 | Day 7 (6 Jul) | Gemini/Groq API calls timing out and hitting rate limits (429) during RAGAS evaluation | Reduced to a single LLM call for faithfulness; used RAGAS SemanticSimilarity (local) for remaining metrics
Sprint 1 | Day 8 (7 Jul) | Browser blocked frontend requests to backend (CORS) | Added CORSMiddleware to FastAPI app
Sprint 1 | Day 9 (8 Jul) | None | N/A
Sprint 1 | Day 10 (9 Jul) | None | N/A
Sprint 2 | Day 2 (14 Jul) | Groq accuracy_agent call raised JSONDecodeError from unescaped double quotes inside LLM-generated evidence text | Instructed model to use single quotes instead of double quotes inside string values; added a retry before falling back to local scoring
Sprint 2 | Day 3 (15 Jul) | Accuracy agent scored a reasonable, non-contradicted claim as 0.0% just because it wasn't explicitly stated in the source | Recalibrated scoring guide to distinguish CONTRADICTED (near 0) from UNSTATED-but-reasonable (partial credit)
Sprint 2 | Day 4 (16 Jul) | Hallucination agent flagged a claim as unsupported even though it appeared verbatim in the retrieved context | Added a code-level grounding safety net that string-matches flagged claims against the raw context and removes false positives
Sprint 2 | Day 5 (17 Jul) | Retrieval returned irrelevant chunks for out-of-domain test questions (e.g. CS topics not in the indexed dataset) | Confirmed via direct retrieve_context() calls which topics are actually indexed; adjusted test cases accordingly
Sprint 2 | Day 7 (19 Jul) | Supabase SQL editor flagged missing Row Level Security on the evaluations table | Ran without RLS, appropriate for a single-user prototype without authentication
Sprint 2 | Day 8 (20 Jul) | git rebase got stuck across multiple sessions; rebase-merge metadata was corrupted | Manually removed .git/rebase-merge and .git/rebase-apply, then completed a clean pull/push
Sprint 2 | Day 8 (20 Jul) | uvicorn command gave Permission denied / command not found in Git Bash | Ran via 'python -m uvicorn' instead of calling the venv executable directly
Sprint 2 | Day 8 (20 Jul) | --reload triggered repeated restart loops after installing new packages (WatchFiles detected changes inside venv) | Accepted as a non-blocking dev-only annoyance; ran without --reload when it stalled
Sprint 2 | Day 6 (18 Jul) | FastAPI raised 'Form data requires python-multipart to be installed' when adding optional PDF upload | Installed python-multipart
Sprint 3 | Day 1 (21 Jul) | None | N/A
Sprint 3 | Day 2 (22 Jul) | None | N/A
Sprint 3 | Day 3 (23 Jul) | None | N/A
Sprint 3 | Day 4 (24 Jul) | Excel-exported CSVs include a hidden BOM character that broke column-name matching on upload | Decoded uploaded CSV bytes with 'utf-8-sig' to strip the BOM before parsing
Sprint 3 | Day 5 (27 Jul) | accuracy_agent still occasionally raised JSONDecodeError on longer, list-heavy answers despite earlier quote-escaping instructions | Added the json_repair library as a tolerant parsing fallback and shortened required output length in the prompt
Sprint 3 | Day 6 (28 Jul) | Hallucination agent flagged simple, correct answers as High risk when retrieval returned irrelevant chunks for general-knowledge questions | Passed reference_answer into detect_hallucination() as an additional source alongside retrieved context
Sprint 3 | Day 7 (29 Jul) | sentence-transformers import chain failed - Windows Smart App Control blocked the xxhash DLL pulled in via the datasets dependency | Downgraded sentence-transformers to 2.7.0 to avoid the blocked dependency chain
Sprint 3 | Day 8 (30 Jul) | uvicorn --reload entered an infinite restart loop unrelated to package installs | Diagnosed as OneDrive background sync touching project files; ran without --reload and noted moving the project outside OneDrive as a future fix
Sprint 3 | Day 9 (30 Jul) | Batch evaluation of a small CSV was noticeably slower than expected | Parallelized the 4 independent per-row agent calls using ThreadPoolExecutor instead of running them sequentially
Sprint 3 | Day 10 (30 Jul) | Batch results table only displayed the question, not the candidate answer being evaluated | Added an Answer column to the batch results table and its rendering logic

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-30 | 2026-07-09 | Ghayathri Devi G M | Testing agent logic with mock/dummy data before calling real APIs | Repeatedly calling live llm APIs | Building end-to-end (input -> retrieval -> evaluation) before adding complexity | Add a mock evaluation function for local testing in Milestone 2 to avoid burning API quota
2 | Sprint 2 | 2026-07-13 | 2026-07-20 | Ghayathri Devi G M | Adding a code-level verification/safety-net layer instead of trusting LLM judge output blindly | Debugging repeatedly against a live LLM API instead of using a mock function first | Building one agent at a time and testing it standalone before wiring into main.py | For Milestone 3, build a mock-response mode for all agents to use while iterating on UI/integration code
3 | Sprint 3 | 2026-07-21 | 2026-08-02 | Ghayathri Devi G M | Running independent agent calls concurrently instead of sequentially for performance | Assuming a code fix was actually saved to disk without verifying file content before debugging further | Adding code-level safety nets (grounding checks, JSON repair) rather than relying solely on prompt instructions | For deployment, test Render's free-tier persistence behavior and move the project outside OneDrive-synced folders to avoid file-watcher issues
4
5
6
7