## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ghayathri Devi G M | 2026-07-03 | HuggingFace dataset load_dataset('squad') failed with HfUriError due to short-form dataset name no longer resolving | Sprint 1 | Ghayathri Devi G M | Others | Switched to namespaced dataset identifier 'rajpurkar/squad' | 2026-07-03 | Closed | Caused by HF Hub API changes, not application logic
2 | Ghayathri Devi G M | 2026-07-05 | RAGAS evaluate() defaulted to OpenAI embeddings internally, raising 'Missing credentials' OpenAIError even though Gemini/Groq was configured as the LLM | Sprint 1 | Ghayathri Devi G M | Logical | Explicitly passed local Sentence-Transformers embeddings (wrapped via LangchainEmbeddingsWrapper) into evaluate() | 2026-07-05 | Closed | RAGAS metrics need embeddings passed separately from the judge LLM
3 | Ghayathri Devi G M | 2026-07-06 | All 4 RAGAS metric jobs raised TimeoutError when calling Gemini API, likely due to default RAGAS timeout/parallel worker settings hitting free-tier rate limits | Sprint 1 | Ghayathri Devi G M | Logical | Added RunConfig(timeout=120-180, max_workers=1, max_retries=2) to slow and serialize calls | 2026-07-06 | Closed | Reduced job concurrency to fit free-tier rate limits
4 | Ghayathri Devi G M | 2026-07-06 | Gemini API returned 'Resource Exhausted' (daily quota) after repeated test runs during debugging | Sprint 1 | Ghayathri Devi G M | Others | Reduced LLM usage to a single call (faithfulness only); all other metrics moved to local RAGAS SemanticSimilarity | 2026-07-07 | Closed | Free-tier daily/per-minute quota exhausted from repeated live testing while debugging
5 | Ghayathri Devi G M | 2026-07-07 | Groq API returned 429 rate-limit error despite only 18% of daily token quota consumed | Sprint 1 | Ghayathri Devi G M | Logical | Identified as a per-minute token burst limit, not daily quota; confirmed correct lightweight model (llama-3.1-8b-instant) was configured | 2026-07-07 | Closed | Distinguish burst/TPM limits from daily/RPD limits when diagnosing 429 errors
6 | Ghayathri Devi G M | 2026-07-08 | Browser blocked frontend (index.html) requests to FastAPI backend with a CORS policy error | Sprint 1 | Ghayathri Devi G M | Standards | Added CORSMiddleware to FastAPI app allowing cross-origin requests from the frontend | 2026-07-08 | Closed | Required since frontend and backend run on different local origins
7 | Ghayathri Devi G M | 2026-07-08 | Swagger UI (/docs) showed 'No parameters' for /evaluate endpoint because raw Request object was used instead of a typed body | Sprint 1 | Ghayathri Devi G M | User Interface | Switched to Body(...) / Pydantic model so FastAPI generates a proper request body form in Swagger | 2026-07-08 | Closed | Improves auto-generated API docs and testability
8 | Ghayathri Devi G M | 2026-07-14 | accuracy_agent.py Groq call raised JSONDecodeError because LLM-generated evidence text contained unescaped double quotes, breaking the JSON response | Sprint 2 | Ghayathri Devi G M | Logical | Instructed the model to use single quotes instead of double quotes inside string values; added a retry attempt before falling back to local similarity scoring | 2026-07-14 | Closed | Small models occasionally violate strict JSON formatting when quoting source text
9 | Ghayathri Devi G M | 2026-07-15 | Accuracy agent scored a reasonable, non-contradicted claim as 0.0% simply because it was not explicitly stated in the retrieved source content | Sprint 2 | Ghayathri Devi G M | Logical | Recalibrated the scoring prompt to classify claims as CONTRADICTED, UNSTATED, or SUPPORTED, reserving 0.0 strictly for direct contradictions | 2026-07-15 | Closed | All-or-nothing scoring was too harsh for claims that are simply unmentioned but not wrong
10 | Ghayathri Devi G M | 2026-07-16 | Hallucination Detection Agent flagged a claim as unsupported even though the exact phrase appeared verbatim in the retrieved context | Sprint 2 | Ghayathri Devi G M | Logical | Added a code-level grounding safety net that string-matches (exact and fuzzy) each LLM-flagged claim against the raw retrieved text and removes false positives automatically | 2026-07-16 | Closed | Small LLM occasionally contradicts itself; verification should not rely on the judge model alone
11 | Ghayathri Devi G M | 2026-07-20 | git rebase became stuck across multiple sessions; 'git rebase --continue' and '--abort' both failed with 'could not read .git/rebase-merge/head-name' | Sprint 2 | Ghayathri Devi G M | Others | Manually deleted .git/rebase-merge and .git/rebase-apply folders, then completed a clean git pull/push | 2026-07-20 | Closed | Rebase metadata was corrupted from an earlier interrupted session
12 | Ghayathri Devi G M | 2026-07-20 | 'uvicorn main:app --reload' failed with Permission denied / command not found in Git Bash (MINGW64) | Sprint 2 | Ghayathri Devi G M | Others | Ran the server via 'python -m uvicorn main:app --reload' instead of invoking the venv executable directly | 2026-07-20 | Closed | Common Windows/Git Bash issue with executables in venv/Scripts
13 | Ghayathri Devi G M | 2026-07-20 | '--reload' entered a restart loop after installing python-multipart, since WatchFiles detected file changes inside the venv folder itself | Sprint 2 | Ghayathri Devi G M | Maintainability | Ran without --reload during package installs; noted --reload-exclude venv/* as a future improvement | 2026-07-20 | Closed | Non-blocking, dev-environment-only issue
14 | Ghayathri Devi G M | 2026-07-18 | FastAPI raised 'Form data requires "python-multipart" to be installed' after adding optional PDF upload via Form/File fields | Sprint 2 | Ghayathri Devi G M | Others | Installed python-multipart | 2026-07-18 | Closed | Required dependency for multipart/form-data parsing, not bundled with FastAPI by default
15 | Ghayathri Devi G M | 2026-07-25 | accuracy_agent.py still occasionally raised JSONDecodeError on longer, list-heavy answers despite earlier single-quote instructions in the prompt | Sprint 3 | Ghayathri Devi G M | Logical | Added the json_repair library as a tolerant parsing fallback and shortened required output length (evidence under 40 words, supporting_excerpt under 20 words) in the prompt | 2026-07-30 | Closed | Prompt instructions alone don't guarantee strict JSON compliance from a small model; a code-level repair layer is more robust
16 | Ghayathri Devi G M | 2026-07-26 | Hallucination Detection Agent flagged simple, correct answers as High risk when ChromaDB retrieval returned irrelevant chunks for general-knowledge questions not well covered by the indexed dataset | Sprint 3 | Ghayathri Devi G M | Logical | Passed reference_answer into detect_hallucination() as an additional source alongside retrieved context, so a valid reference can confirm a claim even when retrieval misses relevant chunks | 2026-07-30 | Closed | A retrieval miss should not cause a false hallucination flag when a valid reference answer already confirms the claim
17 | Ghayathri Devi G M | 2026-07-30 | sentence-transformers import chain failed with 'ImportError: DLL load failed while importing _xxhash' - Windows Smart App Control blocked the xxhash DLL pulled in via the datasets dependency | Sprint 3 | Ghayathri Devi G M | Others | Downgraded sentence-transformers to version 2.7.0 to avoid pulling in the datasets/xxhash dependency chain entirely | 2026-08-02 | Closed | Windows security policy blocked an unsigned native dependency; avoided the dependency rather than disabling an OS security feature
18 | Ghayathri Devi G M | 2026-07-30 | 'uvicorn main:app --reload' entered an infinite restart loop unrelated to package installs this time | Sprint 3 | Ghayathri Devi G M | Maintainability | Diagnosed as OneDrive background sync touching files inside the project folder, which WatchFiles detected as changes; ran without --reload and noted relocating the project outside OneDrive as a future fix | 2026-08-02 | Closed | OneDrive-synced project folders are a known source of file-watcher interference for dev servers
19 | Ghayathri Devi G M | 2026-07-30 | Batch evaluation of a small CSV (5 rows) was noticeably slower than expected, since each row's 4 agent calls ran strictly one after another | Sprint 3 | Ghayathri Devi G M | Maintainability | Parallelized the 4 independent per-row agent calls using ThreadPoolExecutor instead of sequential execution | 2026-08-02 | Closed | I/O-bound LLM calls that don't depend on each other's output benefit significantly from concurrent execution
20 | Ghayathri Devi G M | 2026-07-30 | Batch results table only displayed the question column, not the candidate answer being evaluated | Sprint 3 | Ghayathri Devi G M | User Interface | Added an Answer column to the batch results table and its JavaScript rendering logic | 2026-08-02 | Closed | Reviewers need to see both the question and the answer to interpret per-row scores correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others